## Pending Items
SL No | Task | Start Date | End Date | Status
1 | Design Documentation and review modifications | 2020-06-15 | 2020-07-03 | Done
2 | POC | 2020-06-24 | 2020-07-03 | InProgress

## WBS
WORK BREAKDOWN STRUCTURE FOR IMPLEMN
Module | Asset Tracking Management System
WBS Number | Task Item & Description | Start Date | Due Date | Duration [Man days]
1 | AMS Database creation | 2020-07-06 | 2020-07-10 | 5
1.1 | Creation of tables ,columns
1.2 | Establish relationship among tables
1.3 | Load dummy data
1.4 | Database wrapper classes
2 | Raise Asset request by User/employee | 2020-07-13 | 2020-07-24 | 10
2.1 | Read Asset Id details
2.2 | Asset Request Id generation
2.3 | Asset Status updation
2.4 | DB updation
2.5 | Email Notification flow
2.6 | Replace Asset request
2.7 | Track Asset request Id
3 | IT Admin/team operations | 2020-07-27 | 2020-07-09 | 12
3.1 | Add and Update New Asset
3.2 | View Asset Details
3.3 | Search Asset Details
3.4 | Delete Asset
3.5 | Transfer Asset
3.6 | Allocate Asset
4 | IT Admin/team operations --License Renewal | 2020-07-11 | 2020-08-17 | 5
4.1 | Filter AssetId for license Renewal
4.2 | License renewal operation
4.3 | Updation of DB
5 | IT Admin Operations -Import Asset Data | 2020-08-18 | 2020-08-24 | 5
5.1 | Import Asset Data
6 | IT Admin Operations -Export Asset Data | 2020-08-25 | 2020-08-31 | 5
6.1 | Export Asset Data to xls
6.2 | Export Asset Data to csv
6.3 | Save exported file to lcoal drive
7 | IT Admin Operations -Asset history | 2020-09-01 | 2020-08-11 | 10
7.1 | Search Asset History by criteria
7.2 | Search Asset History without criteria
7.3 | Display Asset History from DB
8 | Asset Manager | 2020-09-14 | 2020-09-21 | 6
8.1 | Asset Id generation
8.2 | Approval of Asset request
8.3 | Rejection of Asset request
9 | Development Environment Set up
9.1 | Configuration |  |  | 2
10 | Unit and Integration testing | 2020-09-22 | 2020-10-03 | 10
|  |  | Total Estimate(Days) | 70